## Slide 1: Agreed Order Kick-Off meeting
January 26, 2021 (1:00-3:00pm)
( Historic Carson Cleaners Store Front)
Notes: Need better picture

## Slide 2: Meeting Purpose
Initiate Agreed Order Negotiations.
Establish Communications Protocols.
Establish Expectations Related to Key Project Documents.

## Slide 3: Agenda
1
Introduction
Project Teams Introduction & Opening Statements
2
Agreed Order Process
3
Key Project Documents
4
Site History, discovery, data gaps
5
Next Steps and Public Comment

## Slide 4: Site Area Map
4701 Brooklyn Ave. NE
Seattle, WA 98105

## Slide 5: Why now?
Washington’s Formal Cleanup Process

## Slide 6: Key Project Documents
Remedial Investigation Work Plan (RIWP)
Agency Review Draft RIWP
Draft RIWP Due Date
Due no later than 90-days after AO Effective date
Final RIWP Due
Final RIWP due 30-days after receipt of Ecology Comments

## Slide 7: Key Project Documents
Remedial Investigation Report (RI)
Agency Review Draft RI Report
60-days after completion of RI Field Work
Remedial investigation validated data uploaded to EIM
Draft RI Due Date
90 days following receipt of remedial investigation validated data
Final RI Report Due
Public Review draft RI Report due 30-days after receipt of Ecology Comments.
Final RI Report 30 days after receipt of Ecology comments, subsequent to public comment

## Slide 8: Key Project Documents
Feasibility Study Report (FS)
Agency Review Draft FS Report
Draft FS Report Due Date
90 days following Ecology approval of Public Review Remedial Investigation Report
Final FS Report Due
Public Review draft FS Report due 30-days after receipt of Ecology Comments.
Final FS Report 30 days after receipt of Ecology comments, subsequent to public comment

## Slide 9: Key Project Documents
Draft Cleanup Action Plan (DCAP)
Agency Review Draft DCAP
Draft DCAP Due Date
Agency Review Draft DCAP
Due 90 days following approval of Public Review draft FS Report
Final FS Report Due
Public Review draft DCAP due 30-days after receipt of Ecology Comments.

## Slide 10: Key Project Meetings
Agreed Order Project Kick-Off Meeting.
Remedial Investigation Planning Meeting
  Will be scheduled during Public Comment Period
  Remedial Investigation Pre-Report Check-in Meeting
  Before the RI Report is submitted to agree on what needs to be included in the report
  Feasibility Study Planning Meeting
  review the preliminary FS Report, provide comment
  Cleanup Action Plan Meeting
  After public review of the RI/FS (if RI/FS goes out Public Comment separate)

## Slide 11: Project History Timeline
1960’s - 2014
Carson Cleaners, Inc. began dry cleaning operations as a tenant in the early 1960’s until 2014,.
2018-2019
As part of an environmental cleanup of the former Chevron 90129 Site across the street from this former dry cleaners, dry cleaning chemicals in the form of halogenated volatile organic compounds
(HVOCs), were discovered in the southwestern portion of the property and along the perimeter of NE 47th Street.
2019

## Slide 12: Project History Timeline
2020
Vapor Intrusion Assessment performed by Anchor

## Slide 13: Chemicals of Concern; Halogenated Volatile Organic Compounds (HVOC)
Chemicals of Concern:
Trichloroethylene (TCE)
Tetrachloroethylene (PCE)
1,1-Dichloroethene and 1,2-Dichloroethene, known collectively as Dichloroethene (DCE)
Vinyl Chloride (VC)

## Slide 14: HVOC in Groundwater
Notes: This figure will be replaced

## Slide 15: Vapor Intrusion Study Sample Locations

## Slide 16: HVOC in Groundwater

## Slide 17: Next Steps
1
Ecology and Tahn Associates will enter into a legal agreement, called and Agreed Order, to being the environmental cleanup.
Agreed Order
2
Complete a site characterization, select a cleanup remedy, and develop the Cleanup Action Plan.
Develop a Cleanup Action Plan
3
Cleanup the remaining contamination.
Implement the Cleanup Action Plan

## Slide 18: Public Participation
Ecology informs the community by:
Mailing a community information sheet to households in the area.
Holding an online public meeting.
Placing a newspaper ad about the comment period in the Seattle Times.
Drafting a Public Participation Plan that outlines how the public is informed about this cleanup site.
Holding a public comment period.

## Slide 19: Out Reach Materials
Ecology prepares Out Reach Documents:
Have drafted Fact Sheet, Display Ad, and Public Participation Plan.
As a courtesy, I will share draft’s for you to review with 30-day response time.
Placing a newspaper ad about the comment period in the Seattle Times.
Holding a public comment period.

## Slide 20: Questions?
Dale Myers, Site Manager
Toxics Cleanup Program
3190 160th Ave SE
Bellevue, WA 98008
Phone #:
425.649.4446
Email:
Dale.Myers@ecy.wa.gov