## Table Template
The annual reporting requirement described in S5.C.7 must follow the format and instructions provided in this appendix.
[9 empty] | Funding (%) |  |  | See: https://apps.ecology.wa.gov/paris/DownloadDocument.aspx?id=279051
KC Agency | Project Name | Project Number | PM | Project Type1 | Start Year | Status2 | End Year | Cost Estimate3 | Local | State | Federal | Basin Area (ac) | LID equiv. Area | LID Point Factor | RT equiv. Area | RT Point Factor | FC Equiv. Area | FC Point Factor | Other Project Area -AC or mi | Other Point Factor | Total SSC Program Points | WQ Benefit (Est. TSS or TS reduction lbs/yr)4 | Hydro Benefit (Est. Avg. % flow reduction)5 | Hydro Benefit Option # | Retrofit Incentive6 | Other Benefit | Monitoring Planned (Y/N) | Lat / Long (X, Y) | Receiving water body name | Comments
WLRD - SWS | Clough Creek Buyout and Sediment Facility |  | W. Kara | 1 | 2013 | 4. Complete/ Maintenance | 2018 | $1.7M | 51 | 7 | 42 | [10 empty] | N/A | N/A | N/A | N/A | Flood reduction | Yes | 47.47354/ -121.78639 | Clough Creek | Construction of facility to capture excess sediment from Clough Creek.
Roads | Isaquah Hobart Road at NE 113th St |  | B. Bacani | 1 | 2013 | 2. Design and permitting | 2014 | $200K | 100 | [12 empty] | N/A | 100 | 2a | 0.75 | None | Yes | 47.48462/ -122.02791 | Issaquah Creek | Provide bioretention.
WTD | Kirkland Pump Station Upgrade |  | S. Yildiz | 1 | 2002 | 3. Construction | 2014 | $75K | 100 | [12 empty] | N/A | 100 | 2a | N/A | None | No | 47.676445/ -122.203728 | Lake Washington | Joint King County-City of Kirkland project. Install silva-cell system to increase infiltration around landscaped area and pervious asphalt paving on the street. Upon completion, the street will be turned over to the City.
WLRD - SWS | Evans Creek Tributary 108 Basin-wide Retrofit Siting |  | C. Jonson | 2 | 2013 | 4. Complete/ Maintenance | 2014 | $300K | 24 | 86 | [11 empty] | N/A | N/A | N/A | N/A | None | Yes | 47.675415/ -122.056882 | Evans Creek | Planning and predesign for three retrofit projects with detention and bioretention stormwater facilities.
WLRD - SWS | May Creek Tributary 291A Small Basin Retrofit |  | C. Jonson | 2 | 2013 | 4. Complete/ Maintenance | 2014 | $216K | 45 | 55 | [11 empty] | N/A | N/A | N/A | N/A | None | Yes | 47.49543/ -122.12522 | May Creek | Planning, predesign, and final design to for one retrofit project with detention and bioretention stormwater facilities.
Transit | North Base Stormwater ISGP Upgrade |  | T. Swanson | 2 | 2013 | 1. Planning | 2015 | $500K | 100 | [12 empty] | N/A | N/A | N/A | 7 | None | Yes | 47.74691/ -122.3013 | Thornton Creek | Additional treatment units installed within an existing stormwater system. Monitoring will take place at outfall.
Roads | Cedar Grove Road Water Quality Pond |  | R. Shular | 2 | 2013 | 4. Complete/ Maintenance | 2014 | $200K | 100 | [12 empty] | N/A | N/A | N/A | 6 | Habitat | Yes | 47.43985/ -122.06384 | Cedar River | Construct water quality pond to reduce sediment load from road. Pit sites along the road have significant track out. Source control enforcement is also being pursued.
Roads | Avondale Rd |  | R. Shular | 2 | 2013 | 2. Design and permitting | 2014 | $150K | 100 | [12 empty] | N/A | 100 | 2a | 0.5 | None | Yes | 47.71543/ -122.09057 | Cottage Creek | Retrofit bioretention swale within right-of-way to treat runoff from high use intersection.
Roads | Kerristan Rd Flow Dispersion |  | R. Shular | 3 | 2013 | 4. Complete/ Maintenance | 2013 | $74K | 100 | [12 empty] | N/A | 100 | 2b | 1.5 | None | Yes | 47.42845/ -121.9294 | Rock Creek | Disperse flow to reduce erosion and increase infiltration.
Roads | Covington-Sawyer Rd at 179 Ave SE |  | D. Bleasedale | 2 | 2013 | 2. Design and permitting | 2015 | $200K | 100 | [12 empty] | N/A | 100 | 2a | 0.25 | None | Yes | 47.295278/ -122.273333 | Soos Creek | Bioretention system.
Roads | Dockton Rd |  | R. Shular | 3 | 2014 | 2. Design and permitting | 2014 | $500K | 100 | [12 empty] | N/A | 100 | 2a | 0.7 | None | Yes | 47.41245/ -122.43744 | Puget Sound | Construct bioinfiltration swale.
Roads | Black Diamond Ravensdale Rd |  | R. Shular | 2 | 2014 | 2. Design and permitting | 2014 | $60K | 100 | [12 empty] | N/A | 100 | 2a | 1 | None | Yes | 47.34711/ -121.98993 | Ground | Construct bioinfiltration swale.
Roads | 140th Avenue SE at SE Petrovitsky Road |  | R. Shular | 2 | 2014 | 5. Project Canelled | 2014 | $100K | 100 | [12 empty] | N/A | N/A | N/A | 1 | None | Yes | 47.44557/ -122.15501 | Cedar River | Enhance existing retention/detention pond to treat runoff from high use intersection.
Roads | Issaquah Hobart Road SE at SE May Valley Road |  | R. Shular | 2 | 2014 | 5. Project Canelled | 2014 | $100K | 100 | [12 empty] | N/A | N/A | N/A | 0.4 | None | Yes | 47.48462/ -122.02791 | Issaquah Creek | Construct water quality swale to treat high use intersection stormwater runoff.
WTD | SMag CSO Control Project Storage Facility |  | S. Namini | 2 | 2014 | 3. Construction | 2015 | $254K | Applied for state funding | [12 empty] | 7.056 | 100 | 2c | 0.49 | None | No | 47.63298/ -122.38664 | Elliott Bay | Landscape infiltration via underdrains; driveway and roof runoff collected and routed to bioswales.
WTD | North Beach Pump Station and CSO Control Facility |  | S. Nanimi | 2 | 2014 | 3. Construction | 2015 | $140K | [13 empty] | 1.152 | N/A | 2c | 0.08 | None | No | 47.701533/ -122.390417 | Puget Sound | State partially funded design. State funding of construction TBD. Area contributing to project for water quality benefit evaluation is drainage area to StormFilter catch basin insert.
WLRD - SWS | Seola Creek Basin Facility Upgrade and Retrofit |  | W. Kara | 3 | 2010 | 4. Complete/ Maintenance | 2015 | $1.5M | 35 | 65 | [11 empty] | 30910.72 | 17.7083 | 1 | 304 | None | Yes | 47.51044/ -122.36880 | Seola Creek | Retrofit to add a wetpool to a flow control facility; partially funded by Ecology Grant 1200062.
WLRD - SWS | Tuscani Facility Remediation |  | C. Jonson | 3 | 2011 | 4. Complete/ Maintenance | 2013 | $124K | 100 | [12 empty] | 118.08 | 100 | 1 | 8.2 | None | Yes | 47.70591/ -122.07458 | Bear Creek | Retrofit of flow control facility to stormwater wetland.
Roads | Military Rd at S 342nd |  | D. Bleasedale | 2 | 2013 | 3. Construction | 2014 | $300K | 100 | [12 empty] | N/A | 100 | 2a | 0.25 | None | Yes | 47.343611/ -122.100833 | Green River | Provide bioretention.
Roads | Kerriston Culvert |  | R. Shular | 5 | 2014 | 4. Complete/ Maintenance | 2014 | $540K | 100 | [12 empty] | N/A | N/A | N/A | 0.25 | Fish passage | Yes | 47.436164/ -121.853633 | Rock Creek | Control overflow from washing fines off gravel road surface; project is one element of a S4.F response undertaken by King County to address stormater impacts caused by this gravel road.
WLRD - SWS | Cedar Valley Facility Remediation |  | C. Jonson | 5 | 2013 | 4. Complete/ Maintenance | 2013 | $77K | 10 | 90 | [11 empty] | 164.16 | 100 | 1 | 11.4 | None | Yes | 47.38643/ -122.01941 | Cedar River | Conversion of a settling pond into a wetpond; partially funded by Ecology Grant G1100216.
WLRD - Rivers | Miller River Home Buyout |  | S. King | 6 | 2010 | 6. Property acquisition |  | $589K | 100 | [12 empty] | N/A | N/A | N/A | N/A | Flood risk reduction | Yes | 47.718092/ -121.395941 | Miller River | Acquire property and remove housing and other structures to eliminate safety hazards near washed out Old Cascade Highway bridge over the Miller River.
WLRD - Rivers | Timber Lane Erosion Buyouts |  | S. King | 6 | 2008 | 6. Property acquisition |  | $2.8M | 100 | [12 empty] | N/A | N/A | N/A | N/A | Flood risk reduction | Yes | 47.714/ -121.319 | South Fork Skykomish | Acquire and remove homes along a stretch of the Skykomish River that are endangered by erosive forces as well as inundation in some places.
WLRD - Rivers | Riverbend Mobile Home Park Acquisition |  | N. Faegenburg | 6 | 2012 | 6. Property acquisition | 2015 | $4.9M | [13 empty] | N/A | N/A | N/A | N/A | Flood risk reduction | Yes | 47.465020/ -122.108913 | Cedar River | Acquire a 100+ unit mobile home park that is prone to flood hazards from overbank flooding, bank erosion, and channel migration. Relocate residents out of harm's way. Setback levee to give the river more room for flood flows, protecting surrounding homes and infrastructure.
WLRD - Rivers | Winkelman Revetment |  | C. Barton | 8 | 2013 | 2. Design and permitting | 2016 | $3.1M | 100 | [12 empty] | N/A | N/A | N/A | N/A | Flood risk reduction | Yes | 47.717/ -122.005 | Snoqualmie River | Repair revetment damages sustained in repeated flood events in order to maintain protection of Seattle Public Utilities Tolt water supply pipeline that runs adjacent to the Snoqualmie River at this location. Riparian restoration component.
WLRD - SWS | May Valley Sediment Removal |  | W. Kameda | 8 | 2010 | 4. Complete/ Maintenance | 2015 | $2.5M | 100 | [12 empty] | N/A | N/A | N/A | N/A | None | Yes | 47.51506/ -122.14282 | May Creek | Sediment removal, large woody debris installation, and buffer restoration.
WLRD - SWS | May Valley, Long Marsh Creek Sediment Removal |  | W. Kameda | 8 | 2010 | 4. Complete/ Maintenance | 2015 | $97K | 100 | [12 empty] | N/A | N/A | N/A | N/A | None | Yes | 47.51455/ -122.13985 | Long Marsh Creek | Sediment removal, large woody debris installation, and buffer restoration.
WLRD - ERES | Dockton Shoreline Restoration |  | L. O'Rollins | 8 | 2011 | 3. Construction | 2014 | $450K |  | 100 | [11 empty] | N/A | N/A | N/A | N/A | Habitat | Yes | 47.03922/ -122.89142 | Puget Sound | Excavation of pocket estuary and riparian revegetation.
WLRD - ERES | Cove Creek |  | L. O'Rollins | 8 | 2012 | 2. Design and permitting | 2016 | $425K | 100 | [12 empty] | N/A | N/A | N/A | N/A | Habitat | Yes | 47.4543/ -122.5096 | Puget Sound | Estuary rehabilitation.
WLRD - ERES | Kanaskat Reach Restoration |  | P. Adler | 8 | 2012 | 4. Complete/ Maintenance | 2014 | $268K | 100 | [12 empty] | N/A | N/A | N/A | N/A | Habitat | Yes | 47.3146/ -121.868 | Green River | Riparian buffer.
WLRD - ERES | Pt Robinson Salt Marsh Reconnection |  | TBD | 8 |  | 1. Planning | 2018 | $740K | [13 empty] | N/A | N/A | N/A | N/A | Habitat | Yes | 47.3892/ -122.3766 | Puget Sound | Salt marsh restoration.
WLRD - ERES | Auburn Narrows Rd Removal/restoration |  | TBD | 8 | 2014 | 1. Planning | [15 empty] | N/A | N/A | N/A | N/A | Habitat | Yes | 47.3031/ -122.1857 | Green River | Buffer restoration.
Roads | Alvord T Bridge Removal |  | T. Ong | 8 | 2010 | 3. Construction | 2014 | $100K | 100 | [12 empty] | N/A | N/A | N/A | 0.25 | None | Yes | 47.369792/ -122.235983 | Green River | Restore riparian cover where bridge was removed and remove pavement.
WLRD - Rivers | Belmondo Revetment Enhancement Project |  | J. Engel | 8 | 2011 | 4. Complete/ Maintenance | 2014 | $1.5M | 100 | [12 empty] | N/A | N/A | N/A | N/A | Flood risk reduction | Yes | 47.450591/ -122.072674 | Cedar River | Continue and complete bank stabilization and flood control work that was initiated during an emergency repair in January 2009 due to flooding. Provide mitigation for impacts to aquatic habitat associated with the Cedar Rapids Levee Setback Repair project.
WLRD - ERES | Elliot Bridge Restoration |  | J. Hansen | 9 | 2013 | 1. Planning | 2016 | $2M |  | 100 | [11 empty] | N/A | N/A | N/A | N/A | Habitat | Yes | 47.4688/ -122.1407 | Cedar River | Wetland and aquatic area creation/mitigation.
WLRD - ERES | Big Spring Creek Restoration |  | F. Nopp | 9 | 2004 | 4. Complete/ Maintenance | 2014 | $2M | 50 |  | 50 | [10 empty] | N/A | N/A | N/A | N/A | Habitat | Yes | 47.2185/ -122.0192 | Newaukum Cr | New channel/floodplain for ditched stream.
WLRD - ERES | Middle Boise - Evans |  | M. Bowles | 9 | 2011 | 4. Complete/ Maintenance | 2013 | $456K | 50 | 10 | 40 | [10 empty] | N/A | N/A | N/A | N/A | Habitat | Yes | 47.1891/ -121.98 | White River | Channel widening and riparian planting.
WLRD - ERES | Upper Carlson |  | D. Eastman | 9 | 2012 | 2. Design and permitting | 2015 | $3.8M | 45 |  | 55 | [10 empty] | N/A | N/A | N/A | N/A | Habitat | Yes | 47.5842/ -121.9075 | Snoqualmie River | Levee setback.
WLRD - ERES | Porter Levee Setback |  | F. Nopp | 9 | 2013 | 2. Design and permitting | 2016 | $4M | 10 |  | 90 | [10 empty] | N/A | N/A | N/A | N/A | Habitat | Yes | 47.2962/ -122.1719 | Green River | Levee setback.
WLRD - ERES | Tolt River Flood Plain Reconnection |  | J. Hansen | 9 | 2007 | 4. Complete/ Maintenance | 2014 | $6.15M | 50 | 25 | 25 | [10 empty] | N/A | N/A | N/A | N/A | Habitat | Yes | 47.6407/ -121.9227 | Snoqualmie River | Levee setback.
WLRD - ERES | Lower Bear Creek Restoration -Klapp |  | L. O'Rollins | 9 | 2014 | 1. Planning | 2016 | $200K | 100 | [12 empty] | N/A | N/A | N/A | N/A | Habitat | Yes | 47.6941/ -122.0923 | Bear Creek | Channel enhancements.
WLRD - Rivers | Tolt River Mile 1.1 Acquisition |  | C. Barton | 9 | 2008 | 6. Property acquisition |  | $5.1M | 100 | [12 empty] | N/A | N/A | N/A | N/A | Flood risk reduction | Yes | 47.642/ -121.906 | Tolt River | Purchase 16 flood and erosion prone parcels and analyze, design and implement a setback of the Tolt 1.1 levee (Hwy to RR Bdg) to reduce flood and channel migration hazards, increase instream sediment storage capacity and flood conveyance, repair natural riverine processes, and reduce future maintenance costs.
WLRD - Rivers | San Souci Neighborhood Buyout |  | S. King | 9 | 2008 | 6. Property acquisition |  | $5.1M | 100 | [12 empty] | N/A | N/A | N/A | N/A | Flood risk reduction | Yes | 47.663/ -121.867 | Tolt River | Remove all homes and a privately-assembled rubble levee at upstream end of the community access road. Also remove homes just upstream and downstream of neighborhood which are at high risk for damage from channel migration.
WLRD - Rivers | Lower Tolt River Acquisition |  | S. King | 9 | 2008 | 6. Property acquisition |  | $656K | 100 | [12 empty] | N/A | N/A | N/A | N/A | Flood risk reduction | Yes | 47.642/ -121.905 | Tolt River | Purchase of property in a flood- and channel migration-prone area along the Lower Tolt River that is subject to considerable development pressure.
WLRD - Rivers | Lower Russell Levee Setback |  | E. Peters | 9 | 2013 | 1. Planning | 2016 | $16.1M | 100 | [12 empty] | N/A | N/A | N/A | N/A | Flood risk reduction | Yes | 47.527/ -122.312 | Green River | Remove and replace existing flood containment system of levee and revetments along the right bank of the Green River in the City of Kent in order to provide long-term flood protection and improve riparian and aquatic habitat.
WLRD - Rivers | Reddington Levee Setback |  | E. Peters | 9 | 2010 | 3. Construction | 2014 | $18.4M | 45 | 55 | [11 empty] | N/A | N/A | N/A | N/A | Flood risk reduction | Yes | 47.338/ -122.209 | Green River | Remove existing Reddington levee and construct a new levee that will be setback from the river’s edge. The levee will be extended north to extend flood protection for a larger area of Auburn and King County.
WLRD - Rivers | Boeing Levee US ACOE ERP |  | A. Levescque | 9 | 2013 | 1. Planning |  | $1M | [13 empty] | N/A | N/A | N/A | N/A | Flood risk reduction | Yes | 47.42194/ -122.26444 | Green River | US ACOE to contribute funds - amount to be determined.
WLRD - Rivers | Briscoe Levee Setback |  | J. Rice | 9 | 2013 | 2. Design and permitting | 2016 | $23.1M | 70 | 30 | [11 empty] | N/A | N/A | N/A | N/A | Flood risk reduction | Yes | 47.43/ -122.258 | Green River | Replace existing Briscoe levee with a new flood protection system.
WLRD - Rivers | Horseshoe Bend Acquisition and Reconnection |  | A. Levescque | 9 |  | 1. Planning |  |  | 100 | [12 empty] | N/A | N/A | N/A | N/A | Flood risk reduction | Yes | 47.361/ -122.23 | Green River | Project on hold. Reconstruct the Horseshoe Bend Levee to a more stable configuration that reduces flood risk to the surrounding areas.
WLRD - Rivers | Countyline to A Street |  | C. Brummer | 9 | 2008 | 2. Design and permitting | 2017 | $14.8M | 70 |  | 30 | [10 empty] | N/A | N/A | N/A | N/A | Flood risk reduction | Yes | 47.263883/ -122.233028 | White River | Construct a new setback levee and revetment and remove portions of the existing Countyline levee in order to reconnect the White River channel with this section of its floodplain, resulting in an increase in flood capacity and restoration of river channel processes. Acquire remaining private property and obtaining easements, conduct detailed design analyses, construct a new setback levee and revetment for flood and erosion protection, create habitat structural components and re-establish a riparian buffer with native vegetation. Pierce County is also contributing approximately 5% of the budget.
WLRD - Rivers | Right Bank Levee Setback |  | C. Brummer | 9 | 2009 | 1. Planning | 2019 | $19.6M | [13 empty] | N/A | N/A | N/A | N/A | Flood risk reduction | Yes | 47.265029/ -122.233889 | White River | Acquire at-risk, flood prone residential properties along the right bank of the White River within the City of Pacific to allow for the construction of a new levee setback flood protection structure. This levee setback will extend from the BNSF railroad bridge embankment to an endpoint at Butte Avenue by White River Estates neighborhood. Acquired residential structures will be removed, temporary sand-filled flood protection barriers will be removed, artificial fill will be excavated, existing wetland areas will be enhanced and an earthen setback levee will be constructed. Budget shares unknown - project is in planning phase, grants applications are currently underway.
WLRD - Rivers | Rainbow Bend Levee Removal and Floodplain Reconnection |  | N. Faegenburg | 9 | 2007 | 2. Design and permitting | 2015 | $2.4M | [13 empty] | N/A | N/A | N/A | N/A | Flood risk reduction | Yes | 47.440236/ -122.065815 | Cedar River | Remove Rainbow Bend levee to allow river flows to spread across the open space created by acquisition of over 50 flood-prone homes. This will slow flood velocities and reduce flood elevations in this area of the river, protecting the adjacent state highway and regional trail. Reduce future maintenance costs, restore natural floodplain functions and improve habitat.
WLRD - Rivers | Willowmoor Floodplain Restoration |  | C. Garric | 9 | 2013 | 2. Design and permitting |  | $1.2M | [13 empty] | N/A | N/A | N/A | N/A | Flood risk reduction | Yes | 47.658448/ -122.118434 | Cedar River | Reconfigure outflow from Lake Sammamish to maintain or reduce current level of flood risk along the lake in a manner that reduces impacts on fish and wildlife in the transition zone between the lake and the river. Anticipate >50% outside funding.
WLRD - Rivers | Rhode Levee Setback |  | N. Faegenburg | 9 |  | 1. Planning |  | $29K | [13 empty] | N/A | N/A | N/A | N/A | Flood risk reduction | Yes | 47.4191/ -122.043 | Cedar River | Following acquisition of the flood-prone homes in this neighborhood, and as part of a long-term flood hazard management strategy, channel conveyance should be expanded to reduce the elevation and intensity of flood flows through this reach while protecting adjacent homes and infrastructure from any increased flood risk. This may be accomplished by setting back the levee or by constructing a conveyance channel through the floodplain.
WLRD - Rivers | Cedar Pre Construction Strategic Acquisition |  | N. Faegenburg | 9 | 2008 | 6. Property acquisition |  | $8.9M | [13 empty] | N/A | N/A | N/A | N/A | Flood risk reduction | Yes | 47.459/ -122.08 | Cedar River | Acquire strategic real estate upon which several large Flood District capital projects are dependent, namely the levee setback projects at the Herzman, Jan Rd, Rutledge-Johnson, Rhode, Getchman, Lower Jones Rd, and Elliot Bridge levee segments.
WLRD - Rivers | Elliot Bridge Levee |  | N. Faegenburg | 9 | 2013 | 1. Planning | 2016 | $2.5M | [13 empty] | N/A | N/A | N/A | N/A | Flood risk reduction | Yes | 47.455085/ -122.083647 | Cedar River | Acquire flood-prone homes in a repetitive loss area spanning both sides of the Cedar River. Levees on both banks will be setback or removed. Eliminate potential for future flood damage to these homes.
WLRD - Rivers | Herzman Levee Setback |  | N. Faegenburg | 9 |  | 1. Planning |  | $48K | [13 empty] | N/A | N/A | N/A | N/A | Flood risk reduction | Yes | 47.465094/ -122.120164 | Cedar River | Remove approximately 350 linear feet of the levee and set back another 190 linear feet in a manner that will reduce risk of flood damage to the levee protecting significant infrastructure on the opposite side of the river, as well as reconnect the river with its floodplain without increasing flood risks to the existing homes or Jones Road.
WLRD - Rivers | Jan Rd - Rutledge Levee Setback |  | N. Faegenburg | 9 |  | 1. Planning |  | $15K | [13 empty] | N/A | N/A | N/A | N/A | Flood risk reduction | Yes | 47.425233/ -122.048479 | Cedar River | Either setback or remove potions of the Jan Road and Rutledge-Johnson Levees in order to reduce potential damage to the downstream Cedar River Trail Levee, which protects portions of both the Cedar River Trail and the Maple Valley Highway. Design such that equivalent or better flood protection remains for the houses remaining behind the levees.
WLRD - Rivers | Tolt River Natural Area Acquisition |  | S. King | 9 | 2008 | 6. Property acquisition |  | $4.6M | 100 | [12 empty] | N/A | N/A | N/A | N/A | Flood risk reduction | Yes | 47.647/ -121.881 | Tolt River | Acquire up to 12 properties in the channel migration zone of the Tolt River in the vicinity of the Tolt Natural Area. Assess the feasibility of removing the Edenholm levee which is currently disconnecting a side channel from being active.
WLRD - Rivers | Alpine Manor Mobile Park Acquisistion |  | S. King | 9 | 2008 | 6. Property acquisition |  | $2.9M | 100 | [12 empty] | N/A | N/A | N/A | N/A | Flood risk reduction | Yes | 47.514248/ -121.922206 | Raging River | Acquire and remove most, if not all, of the homes in the Alpine Manor Mobile Home Park, as well as several single family homes in the area, and restore the riparian area to support salmon recovery.
Roads | Jones Rd overflow control |  | R. Shular | 11 | 2013 | 1. Planning | 2014 | $100K | 100 | [12 empty] | N/A | N/A | N/A | 0.25 | None | Yes | 47.45882/ -122.07685 | Cedar River | Control flow from washing road surface pollutants and reduce sediment load.
Roads | Peasley Canyon |  | R. Shular | 11 | 2014 | 2. Design and permitting | 2014 | $150K | 100 | [12 empty] | N/A | N/A | N/A | 0.25 | None | Yes | 47.305772/ -122.274197 | Green River | Stabilze embankment from washing sediment into road.
Roads | Riverbend |  | R. Shular | 11 | 2013 | 4. Complete/ Maintenance | 2013 | $19K | 100 | [12 empty] | N/A | N/A | N/A | 0.25 | None | Yes | 47.46367/ -121.74597 | Snoqualmie River | Control flow from washing road surface pollutants and reduce sediment load.
Roads | NE Stossel Ck Wy |  | R. Shular | 11 | 2013 | 4. Complete/ Maintenance | 2013 | $10K | 100 | [12 empty] | N/A | N/A | N/A | 0.25 | None | Yes | 47.7219/ -121.8769 | Stossel Creek | Control flow from washing road surface pollutants and reduce sediment load.
Roads | Money Creek Rd |  | R. Shular | 11 | 2013 | 4. Complete/ Maintenance | 2013 | $14K | 100 | [12 empty] | N/A | N/A | N/A | 0.25 | None | Yes | 47.71347/ -121.4098 | Money Creek | Control flow from washing road surface pollutants and reduce sediment load.
Roads | SE David Powell Road Drainage Improvement |  | R. Shular | 11 | 2014 | 2. Design and permitting | 2014 | $60K | 100 | [12 empty] | N/A | N/A | N/A | 0.25 | None | Yes | 47.557978/ -121.887242 | Snoqualmie River | Control flow from washing road surface pollutants and reduce sediment load.
Roads | Middle Fork Drainage Improvement |  | R. Shular | 11 | 2014 | 2. Design and permitting | 2014 | $15K | 100 | [12 empty] | N/A | N/A | N/A | 0.25 | None | Yes | 47.46918/ -121.66985 | Snoqualmie River | Control flow from washing road surface pollutants and reduce sediment load.
Roads | Wilderness Rim |  | R. Shular | 11 | 2014 | 2. Design and permitting | 2014 | $60K | 100 | [12 empty] | N/A | N/A | N/A | 0.25 | None | Yes | 47.44603/ -121.77761 | Snoqualmie River | Control flow from washing road surface pollutants and reduce sediment load.
Roads | North Fork Road Drainage Improvement |  | R. Shular | 11 | 2014 | 2. Design and permitting | 2014 | $15K | 100 | [12 empty] | N/A | N/A | N/A | N/A | None | Yes | 47.55748/ -121.74087 | Snoqualmie River | Stabilize muddy shoulder to reduce sediment washoff to stream.
WLRD - SWS | Aging Pipe Replacement Program |  | R. Berryessa | 11 | 2013 | 1. Planning | 2018 | $950K | 100 | [12 empty] | N/A | N/A | N/A | N/A | None | Yes | TBD | TBD | ID pipes throughout the County for replacement; capital costs exceed $25,000 per site.
WLRD - SWS | Fairwood 11 Pipe Replacement |  | R. Berryessa | 11 | 2013 | 2. Design and permitting | 2020 | $1.25M | 100 | [12 empty] | N/A | N/A | N/A | N/A | Flood risk reduction & Fish passage | Yes | 47.45479/ -122.16306 | Molasses Creek | Replacement of a deteriorating facility discharge pipe that also functions as in-line flow control.
Roads | South Park Bridge |  | J. Sussex | 12 | 2013 | 3. Construction | 2014 | $400K | 100 | [12 empty] | N/A | 100 | 2a | 0.25 | Ed & outreach | Yes | 47.530106/ -122.314144 | Duwamish River | Provide biofiltraton to treat road runoff.
Parks | Lakewood Park |  | D. Sizemore | 12 | 2013 | 4. Complete/ Maintenance | 2013 | $50K | 16% local, 84% private | [12 empty] | 478.4 | 100 | 1 | 1.5 | None | No | 47.5055/ -122.3424 | Lake Hicks | Installation of infiltration trenches for new Technical Access building constructed.
SWD | Factoria Recycling & Xfer Stn - Detention Vault |  | G. Ugwoaba | 12 | 2010 | 2. Design and permitting | 2018 | $1.4M | 100 | [12 empty] | N/A | 100 | 2a | 11.2 | None | Yes | 47.5824N/ -122.15989W | East Creek | Construction of detention vault (approx 1.5 million gallons).
SWD | Factoria Recycling & Xfer Stn - Permeable Pavement |  | G. Ugwoaba | 12 | 2010 | 2. Design and permitting | 2018 | $55K | 100 | [12 empty] | N/A | 100 | 2a | 0.35 | None | Yes | 47.5824N/ -122.15989W | East Creek | Installation of permeable pavement.
SWD | Factoria Recycling & Xfer Stn - Filtera System |  | G. Ugwoaba | 12 | 2010 | 2. Design and permitting | 2018 | $30K | 100 | [12 empty] | N/A | 100 | 2a | 0.63 | None | Yes | 47.5824N/ -122.15989W | East Creek | Installation of Filtera systems.
SWD | Factoria Recycling & Xfer Stn - Amended Sand Filter Vault |  | G. Ugwoaba | 12 | 2010 | 2. Design and permitting | 2018 | $325K | 100 | [12 empty] | N/A | 100 | 2a | 7.175 | None | Yes | 47.5824N/ -122.15989W | East Creek | Installation of sand filter vault.
SWD | Factoria Recycling & Xfer Stn - Rain Water Harvesting |  | G. Ugwoaba | 12 | 2010 | 2. Design and permitting | 2018 | $290K | 100 | [12 empty] | N/A | 100 | 2a | 1.7675 | None | Yes | 47.5824N/ -122.15989W | East Creek | Rain water harvesting.
Parks | Redmond Ridge Field Conversion |  | D. Sizemore | 12 | 2014 | 4. Complete/ Maintenance | 2014 | $100K | 46% local, 54% private | [12 empty] | 43.2 | N/A | N/A | 5.25 | None | No | 47.6719/ -122.0352 | Bear Creek | Installation of Stormfilter treatment system for sand fields converted to field turf.
Parks | Ravensdale Field Conversion |  | D. Sizemore | 12 | 2013 | 4. Complete/ Maintenance | 2013 | $50K | 74% local, 26% private | [12 empty] | 43.2 | N/A | N/A | 5.25 | None | No | 47.3574/ -121.9816 | Rock Creek | Installation of Stormfilter treatment system for sand fields converted to field turf.
Parks | Ravensdale Field Addition |  | D. Sizemore | 12 | 2014 | 3. Construction | 2014 | $100K | 66% local, 12% state, 22% private | [12 empty] | 86.4 | N/A | N/A | 10.5 | None | No | 47.3574/ -121.9816 | Rock Creek | Installation of Stormfilter treatment system for new field turf fields.
Parks | Big Finn Lacrosse Field Conversion |  | D. Sizemore | 12 | 2013 | 4. Complete/ Maintenance | 2013 | $75K | 100% private | [12 empty] | 43.2 | N/A | N/A | 4.5 | None | No | 47.7237/ -122.2374 | Denny Creek | Installation of sand filter for converting grass soccer field to field turf.
Parks | Petrovitsky Park |  | D. Sizemore | 12 | 2013 | 4. Complete/ Maintenance | 2013 | $75K | 14% local, 45% state, 41% private | [12 empty] | 72 | N/A | N/A | 7.5 | None | No | 47.4411/ -122.1178 | Cedar River | Installation of sand filter for converting sand soccer fields to field turf.
Parks | Black Diamond |  | D. Sizemore | 12 | 2013 | 3. Construction | 2015 | 25K | 100 | [12 empty] | 14.4 | 100 | 2b | 1.75 | None | No | 47.3362/ -122.0135 | Covington Creek | Installation of parking lot and water quality treatment & flow dispersion.
Parks | Taylor Mountain |  | D. Sizemore | 12 | 2014 | 2. Design and permitting | 2015 | 40K | 30 | 70 | [11 empty] | 43.2 | 100 | 2b | 4.5 | None | No | 47.4324/ -121.9713 | Issaquah Creek | Installation of parking lot and water quality treatment & flow dispersion.
Parks | Pinnacle Peak |  | D. Sizemore | 12 | 2014 | 2. Design and permitting | 2016 | 75K | 50 | 50 | [11 empty] | 72 | 100 | 2b | 7.5 | None | No | 47.1680/ -121.9871 | White River | Installation of parking lot and water quality treatment & flow dispersion.
Parks | Duthie Hill |  | D. Sizemore | 12 | 2013 | 3. Construction | 2014 | 215K | 50 | 50 | [11 empty] | 72 | 100 | 2b | 7.5 | None | No | 47.5727/ -121.9883 | Lake Sammamish | Installation of parking lot and water quality treatment & flow dispersion.
WLRD - SWS | Horseshoe Lake |  | W. Kameda | 12 | 2010 | 2. Design and permitting | 2016 | 872K | 100 | [12 empty] | N/A | N/A | N/A | N/A | None | Yes | 47.31044/ -122.03933 | Green River | Construction of conveyance pipe to carry flood water from Horseshoe Lake to either a temporary receiving area in Black Diamond or to a yet to be construction Regional Stormwater Facility. This is a conveyance only project.
WLRD - SWS | Fairwood 4 Stormwater Improvement |  | D. Sizemore | 12 | 2013 | 2. Design and permitting | 2017 | $1.5M | 50 | 50 | [11 empty] | N/A | N/A | N/A | N/A | None | Yes | 47.45763/ -122.16081 | Molasses Creek | Replacement of a deteriorating discharge pipe.
WLRD- SWS | Evans Creek Tributary 108 Detention Vault Retrofits | 1128113 | Johnson, Claire | 2 | 2016 | 4. Complete/ Maintenance | 2018 | 670000 | 28 | 72 | [11 empty] | 32 | 100 | 1 | 1 | None | Yes | 47.67299/ -122.06376 | Evans Creek | Design and constuct two stromwater retrofit detention vaults in right of way, in front of addresses 20620 and 20626 NE 76th Place and 20508 NE 78th Street. Partially funded by Ecology Grant WQC-2016-KCWLRD-00056.
WLRD- SWS | DES FMD BURIEN DC WQ IMPROVEMT | 1136642 | McNair, Matt | 4 |  | 2. Design and permitting |  | 1119000 |  |  |  | 2.494 | [9 empty] | TBD: 47.469957, -122.342485; TBD: Miller-Walker Creek | Retrofit and expand an existing detention cell to two bioretention (infiltration) cells. Treats adjacent parking lot and Burien City ROW.
WLRD- SWS | WLSWCWQ EVANS CK TRIB108DTNTN | 1129499 | McNair, Matt | 2 |  | 2. Design and permitting |  | 326000 |  |  |  | 4.15 | [9 empty] | TBD: 47.674644, -122.065161; TBD: Evans Creek | Design and constuct stromwater retrofit detention vault in right of way, in front of addresses 20650 through 20690 NE 79th Street.
WLRD- SWS | May Creek Tributary 291A Stormfilter Retrofit | 1128032 | McNair, Matt | 2 | 2016 | 5. Project Canelled | 2020 | 141000 | 45 | 55 | [11 empty] | 14 | N/A | N/A | 1 | None | No | 47.48626/ -122.12312 | May Creek | Design and construct a StormFilter system in right of way in front of parcel 3243200030 near Renton, WA. Grant was awarded by Ecology. Grant declined by KC due to use of proprietary equipment.
WLRD- SWS | WLSWCWQ MAYCK TRIB291A CMTRY | 1129498 | McNair, Matt | 3, 4, 5, 7, 9, 10 |  | 2. Design and permitting |  | 330000 |  |  |  | 102.5 | [9 empty] | TBD: 47.48671, -122.12154; TBD: May Creek | Improved Stormwater Management through; Design of Bioswalt to treat ROW runoff, retrofit existing DR0509 facility, Property Purchase/conservation, Wetland Restoration (wetland buffer), Removal of fill (floodplain detention volume expansion), removal of impervious surface
WLRD- SWS | WLSWCWQ MIL CK TRIB51 DESIGN | 1129500 | McNair, Matt | 2/3/4 |  | 1. Planning |  | 312000 |  |  |  | 49.1 | [9 empty] | TBD: 47.338194, -122.280097 OR 47.3350389, -122.2906077; TBD: Mill Creek | Design a BMP to improve Water Volume & Quality management within the basin (could be new facility, or retrofit of existing)
WLRD- SWS | Wilderness Rim Pond Access Berm |  |  | 5 | 2016 | 4. Complete/ Maintenance | 2016 | $40K | 60 |  | 40 | [10 empty] | N/A | N/A | N/A |  | Flood reduction | No | 47.444557/ -121.773907 | Snoqualmie River | Berm to protect nearby residential properties and associated septic systems from infiltration pond overflow. FEMA grant E15-170
WLRD- SWS | Wilderness Rim Berm and Pond Excavation |  |  | 5 | 2016 | 3. Construction | 2016 | $235K | 60 |  | 40 | [10 empty] | N/A | N/A | N/A |  | Flood reduction | No | 47.444557/ -121.773907 | Snoqualmie River | Berm to protect nearby residential properties and associated septic systems from infiltration pond overflow. FEMA grant E15-170
WLRD | Cedar River, Byers Road |  |  | 5 | 2019 | 6. Property acquisition | 2019 | 682500 | 100 |  |  | 1.27 | [8 empty] | 0.635 | N/A: N/A; N/A: N/A
WLRD | Big Spring/Newaukum Creek Natural Area |  |  | 5 | 2019 | 6. Property acquisition | 2019 | 465000 | 100 |  |  | 10 | [8 empty] | 5 | N/A: N/A; N/A: N/A
WLRD | Slippery Creek |  |  | 5 | 2019 | 6. Property acquisition | 2019 | 99000 | 100 |  |  | 2.18 | [8 empty] | 1.09 | N/A: N/A; N/A: N/A
WLRD | Re-Greening the Green |  |  | 5 | 2019 | 6. Property acquisition | 2019 | 46000 | 100 |  |  | 0.82 | [8 empty] | 0.41 | N/A: N/A; N/A: N/A
WLRD | Taylor Creek Mitigation |  |  | 5 | 2019 | 6. Property acquisition | 2019 | 2500 | 100 |  |  | 0.065 | [8 empty] | 0.0325 | N/A: N/A; N/A: N/A
WLRD | Cougar Mountain |  |  | 5 | 2019 | 6. Property acquisition | 2019 | 355436 | 100 |  |  | 12.5 | [8 empty] | 6.25 | N/A: N/A; N/A: N/A
WLRD | Middle Bear Creek Natural Area |  |  | 5 | 2019 | 6. Property acquisition | 2019 | 126500 | 100 |  |  | 5.16 | [8 empty] | 2.58 | N/A: N/A; N/A: N/A
WLRD | Cedar River |  |  | 5 | 2019 | 6. Property acquisition | 2019 | 630000 | 100 |  |  | 1.21 | [8 empty] | 0.605 | N/A: N/A; N/A: N/A
WLRD | Snoqualmie Valley TDR |  |  | 5 | 2019 | 6. Property acquisition | 2019 | 885000 | 100 |  |  | 68.6 | [8 empty] | 34.3 | N/A: N/A; N/A: N/A
WLRD | Paradise Valley Natural Area |  |  | 5 | 2019 | 6. Property acquisition | 2019 | 50000 | 100 |  |  | 4.25 | [8 empty] | 2.125 | N/A: N/A; N/A: N/A
WLRD | Mouth of Taylor Reach Natural Area |  |  | 5 | 2019 | 6. Property acquisition | 2019 | 0 | 100 |  |  | 2.78 | [8 empty] | 1.39 | N/A: N/A; N/A: N/A
WLRD | Judd Creek Natural Area |  |  | 5 | 2019 | 6. Property acquisition | 2019 | 45000 | 100 |  |  | 3.5 | [8 empty] | 1.75 | N/A: N/A; N/A: N/A
WLRD | Vashon Farmland |  |  | 5 | 2019 | 6. Property acquisition | 2019 | 286000 | 100 |  |  | 12.44 | [8 empty] | 6.22 | N/A: N/A; N/A: N/A
WLRD | Cedar River |  |  | 5 | 2019 | 6. Property acquisition | 2019 | 275000 | 100 |  |  | 2.85 | [8 empty] | 1.425 | N/A: N/A; N/A: N/A
WLRD | Big Spring/Newaukum Creek Natural Area |  |  | 5 | 2019 | 6. Property acquisition | 2019 | 510000 | 100 |  |  | 3.9 | [8 empty] | 1.95 | N/A: N/A; N/A: N/A
WLRD | Cemetery Pond |  |  | 5 | 2019 | 6. Property acquisition | 2019 | 110000 | 100 |  |  | 0.37 | [8 empty] | 0.185 | N/A: N/A; N/A: N/A
WLRD | Shake Mill Left Bank Levee |  |  | 5 | 2019 | 6. Property acquisition | 2019 | 9600 | 100 |  |  | 0.37 | [8 empty] | 0.185 | N/A: N/A; N/A: N/A
WLRD | Fall City Buyouts |  |  | 5 | 2019 | 6. Property acquisition | 2019 | 654500 | 100 |  |  | 0.6 | [8 empty] | 0.3 | N/A: N/A; N/A: N/A
WLRD | May Creek Tributary 291A |  |  | 5 | 2019 | 6. Property acquisition | 2019 | 210000 | 100 |  |  | 3.5 | [8 empty] | 1.75 | N/A: N/A; N/A: N/A
WLRD | Cemetery Pond |  |  | 5 | 2019 | 6. Property acquisition | 2019 | 150000 | 100 |  |  | 0.8 | [8 empty] | 0.4 | N/A: N/A; N/A: N/A
WLRD | Big Spring/Newaukum Creek Natural Area |  |  | 5 | 2019 | 6. Property acquisition | 2019 | 35000 | 100 |  |  | 1.61 | [8 empty] | 0.805 | N/A: N/A; N/A: N/A
WLRD | Shake Mill Left Bank Levee |  |  | 5 | 2019 | 6. Property acquisition | 2019 | 10000 | 100 |  |  | 0.53 | [8 empty] | 0.265 | N/A: N/A; N/A: N/A
WLRD | Fairwood No. 11 | 1117559 | R Berryessa | 4 | 2019 | Final Design | 2019 | 1000000 | 100 | [11 empty] | 0 | N/A: N/A; N/A: N/A; TBD: Molasses Cr
WLRD | Paradise Valley Natural Area |  |  | 5 | 2019 | 6. Property acquisition | 2019 | 45000 | 100 |  |  | 3 | [8 empty] | 1.5 | N/A: N/A; N/A: N/A
WLRD | Mitchell Hill |  |  | 5 | 2019 | 6. Property acquisition | 2019 | 430000 | 100 |  |  | 40.59 | [8 empty] | 20.295 | N/A: N/A; N/A: N/A
WLRD | Lake to Sound Trail |  |  | 5 | 2019 | 6. Property acquisition | 2019 | 10485 | 100 |  |  | 0.008 | [8 empty] | 0.004 | N/A: N/A; N/A: N/A
WLRD | Mud Creek Restoration - Acquisition | 1132403 | Kara, Wendy | 5 | 2019 | 6. Property acquisition | 2019 | 635000 | 100 |  |  | 2.75 | [8 empty] | 1.375 | N/A: N/A; N/A: N/A
WLRD | TDR Farmland Easement |  |  | 5 | 2019 | 6. Property acquisition | 2019 | 27500 | 100 |  |  | 6.38 | [8 empty] | 3.19 | N/A: N/A; N/A: N/A
WLRD | Parks Trail Easement |  |  | 5 | 2019 | 6. Property acquisition | 2019 | 11000 | 100 |  |  | 0.54 | [8 empty] | 0.27 | N/A: N/A; N/A: N/A
WLRD | Patterson Creek Natural Area |  |  | 5 | 2019 | 6. Property acquisition | 2019 | 420000 | 100 |  |  | 49.23 | [8 empty] | 24.615 | N/A: N/A; N/A: N/A
WLRD | Wayne Golf Course, Back Nine |  |  | 5 | 2019 | 6. Property acquisition | 2019 | 0 | 100 |  |  | 31.38 | [8 empty] | 15.69 | N/A: N/A; N/A: N/A
WLRD | Lower Newaukum Creek Natural Area |  |  | 5 | 2019 | 6. Property acquisition | 2019 | 495000 | 100 |  |  | 40 | [8 empty] | 20 | N/A: N/A; N/A: N/A
WLRD | Green River Tukwila |  |  | 5 | 2019 | 6. Property acquisition | 2019 | 1750000 | 100 |  |  | 1.48 | [8 empty] | 0.74 | N/A: N/A; N/A: N/A
WLRD | Vashon-Paradise Valley |  |  | 5 | 2019 | 6. Property acquisition | 2019 | 0 | 100 |  |  | 5.23 | [8 empty] | 2.615 | N/A: N/A; N/A: N/A
WLRD | Cougar Mountain Regional Wildland |  |  | 5 | 2019 | 6. Property acquisition | 2019 | 600000 | 100 |  |  | 10 | [8 empty] | 5 | N/A: N/A; N/A: N/A
WLRD | Green River Natural Area |  |  | 5 | 2019 | 6. Property acquisition | 2019 | 153000 | 100 |  |  | 5.98 | [8 empty] | 2.99 | N/A: N/A; N/A: N/A
WLRD | Lower Cedar River Natural Area |  |  | 5 | 2019 | 6. Property acquisition | 2019 | 0 | 100 |  |  | 10.9 | [8 empty] | 5.45 | N/A: N/A; N/A: N/A
WLRD | White River |  |  | 5 | 2019 | 6. Property acquisition | 2019 | 108000 | 100 |  |  | 0.12 | [8 empty] | 0.06 | N/A: N/A; N/A: N/A
WLRD | Mallard Bay Trail Easement |  |  | 5 | 2019 | 6. Property acquisition | 2019 | 0 | 100 |  |  | 0.14 | [8 empty] | 0.07 | N/A: N/A; N/A: N/A
WLRD | Tolt River Mile 1.1 |  |  | 5 | 2019 | 6. Property acquisition | 2019 | 40000 | 100 |  |  | 0.65 | [8 empty] | 0.325 | N/A: N/A; N/A: N/A
WLRD | Molasses Creek | ? | R Berryessa |  | 2019 | 6. Property acquisition | 2019 | 0 | 100 |  |  | 1.48 | [8 empty] | 0.74 | N/A: N/A; N/A: N/A
WLRD | Big Spring/Newaukum Creek Natural Area |  |  | 5 | 2019 | 6. Property acquisition | 2019 | 27500 | 100 |  |  | 3.6 | [8 empty] | 1.8 | N/A: N/A; N/A: N/A
WLRD | Snoqualmie: Hafner Levee Setback |  |  | 5 | 2019 | 6. Property acquisition | 2019 | 475000 | 100 |  |  | 38.52 | [8 empty] | 19.26 | N/A: N/A; N/A: N/A
WLRD | Cougar Mountain Regional Wildland |  |  | 5 | 2019 | 6. Property acquisition | 2019 | 93500 | 100 |  |  | 2.5 | [8 empty] | 1.25 | N/A: N/A; N/A: N/A
WLRD | Paradise Lake Natural Area |  |  | 5 | 2019 | 6. Property acquisition | 2019 | 420000 | 100 |  |  | 10.02 | [8 empty] | 5.01 | N/A: N/A; N/A: N/A
WLRD | Paradise Lake Natural Area |  |  | 5 | 2019 | 6. Property acquisition | 2019 | 320000 | 100 |  |  | 8.4 | [8 empty] | 4.2 | N/A: N/A; N/A: N/A
WLRD | Point Heyer Natural Area |  |  | 5 | 2019 | 6. Property acquisition | 2019 | 850000 | 100 |  |  | 2.78 | [8 empty] | 1.39 | N/A: N/A; N/A: N/A
WLRD | White Center Stormwater Facility Retrofit | 1133946 | Kameda, Wes | 4 |  | 1. Planning |  | 600000 |  |  |  | 150 | [8 empty] | 75 | TBD: 47.515349, 122.349445; TBD: Salmon Creek
WLRD | Ravensdale Stormwater Facility Retrofit | 1133944 | Kameda, Wes | 4 |  | 2. Design and permitting |  | 200000 |  |  |  | 20 | [8 empty] | 10 | TBD: 47.34057, -121.9216; TBD: Rock Creek
| Notes | [20 empty] | N/A: 2 Status (as of December 31st of the reporting year) | 5 Hydro Benefit
| N/A - not available or not applicable | [20 empty] | N/A: 1. Planning | 1. Project's volume ratio
| WQ - water quality | [20 empty] | N/A: 2. Design and permitting | 2a. 100%
| TSS - total suspeded solids | [20 empty] | N/A: 3. Construction | 2b. 100%
| TS - total solids | [20 empty] | N/A: 4. Complete/ Maintenance | 2c. Project's volume ratio
| FEMA - Federal Emergency Management Agency | [20 empty] | N/A: 5. Project Cancelled | 6 Retrofit Incentive - From Washington State Department of Ecology Retrofit Incentive Table
6. Property acquisition
| 1 Type | [20 empty] | N/A: 3 Cost Estimate - Costs to be updated to reflect final costs when Status 4 or 6 is reached.
| 1. New flow control facility | [20 empty] | N/A: 4 WQ Benefit - KC S8.d loading rates used for LDR, HDR, Commercial land use types
2. New runoff treatment facility (or treatment and flow control facility)
3. New LID BMPs
4. Retrofit of existing treatment and/or flow control facility
5. Property acquisition
6. Maintenance with capital construction costs ≥ $25,000
7. Restoration of riparian buffer
8. Restoration of forest cover
9. Floodplain reconnection projects
10. Removal of impervious surfaces
11. Other actions to address stormwater runoff into or from the MS4 not otherwise required in S5.C.
Note on H99: Lai, Lorraine: Grant not awarded

## Retrofit Incentive Table (hidden)
Fill in all yellow fields according to the directions provided.
Retrofit Incentive Table
Project Achievement | Incentive Points
Water Quality: Better than Existing | 100 (as % of impervious area served by the project)
Water Quality: Better than Existing in known water quality problem area | 150 (as % of impervious area served by the project)
Water Quality: Basic Treatment | 150 (as % of impervious area served by the project)
Water Quality: Enhanced Treatment | 175 (as % of impervious area served by the project)
Water Quality: Meets WQ standards for target pollutant (assumed to be > level of treatment than enhanced) | 200 (as % of impervious area served by the project)
Flow Control: Better than Existing | 100 (as % of impervious area served by the project)
Flow Control: Meets duration standard for Pasture | 125 (as % of impervious area served by the project)
Flow Control: Meets duration standard for Forest | 150 (as % of impervious area served by the project)
Flow Control: Protects habitat or prevents erosion and scour in a known flow control problem area | 150 (as % of impervious area served by the project)
Flow Control: Meets LID Performance Standard | 200 (as % of impervious area served by the project)
Maintenance with capital construction costs $25,000 or other maintenance actions per S5.C.6.a.ii(5) | 25 (as % of the area served by the maintenance activity)
Riparian Habitat Acquisition | 50 (as % of acres acquired)
Restoration of Forest Cover | 25 (as % of acres restored)
Restoration of Riparian Buffer | 25 (as % of acres restored)
Retrofit Incentive Formula: Retrofit Incentive = Incentive Points (as decimal) x applicable area (in acres)
Example: WQ retrofit project (XYZ Pond) is designed to provide better than existing WQ treatment and flow control to meet standard for forest and serves 0.23 acres: 1.5 x 0.23 = 0.345 (Example provides both treatment and flow control with greater multiplier used).
Project Name | Incentive Points
Cedar Valley Facility Remediation | 100%
Seola Creek Basin Facility Upgrade and Retrofit | 100%
Tuscani Facility Remediation | 100%
Evans Creek Tributary 108 Basin Wide Retrofit Siting | 100%
May Creek Tributary 291A Small Basin Retrofit | 100%
Aging Pipe Replacement Program | 25%
Fairwood 11 Pipe Replacement | 25%
Fairwood 11 Regional Facility Remediation | 100%
May Valley Sediment Removal | 25%
May Valley, Long Marsh Creek Sediment Removal | 25%
Clough Creek Buyout and Sediment Facility | 100%
North Base Stormwater ISGP Upgrade | 100%
Dockton Shoreline Restoration | 25%
Elliot Bridge Restoration | 25%
Big Spring Creek Restoration | 25%
Middle Boise - Evans | 25%
Upper Carlson | 25%
Cove Creek | 25%
Porter Levee Setback | 25%
Kanaskat Reach Restoration | 25%
Pt Robinson Salt Marsh Reconnection | 25%
Auburn Narrows Rd Removal/restoration | 25%
Tolt River Flood Plain Reconnection | 25%
Lower Bear Creek Restoration -Klapp | 25%
Cedar Grove Road Water Quality Pond (1122355) | 150%
Avondale Rd (1122356) | 100%
Riverbend (1121224) | 100%
Military Rd at S 342nd | 100%
South Park Bridge | 100%
NE Stossel Ck Wy (1121701) | 100%
Money Creek Rd (1121702) | 100%
Kerristan Rd flow dispersion (1121776) | 150%
Jones Rd overflow control (1122907) | 100%
Kerriston Culvert (1122354) | 100%
Covington-Sawyer Rd at 179 Ave SE | 100%
Peasley Canyon (1122909) | 100%
SE David Powell Road Drainage Improvement | 100%
Alvord T Bridge Removal | 100%
1122911 Middle Fork Drainage Improvement | 100%
1122912 Wilderness Rim | 100%
1123183 Dockton Rd | 100%
1123184 Black Diamond Ravensdale Rd | 100%
1122910 North Fork Road Drainage Improvement | 100%
Isaquah Hobart Road at NE 113th St | 150%
140th Avenue SE at SE Petrovitsky Road | 100%
Issaquah Hobart Road SE at SE May Valley Road | 100%
Factoria Recycling & Xfer Stn - Detention Vault | 175%
Factoria Recycling & Xfer Stn - Permeable Pavement | 175%
Factoria Recycling & Xfer Stn - Filtera System | 175%
Factoria Recycling & Xfer Stn - Amended Sand Filter Vault | 175%
Factoria Recycling & Xfer Stn - Rain Water Harvesting | 175%
SMag CSO Control Project Storage Facility | 100%
Kirkland Pump Station Upgrade project | 100%
North Beach Pump Station and CSO Control Facility | 100%
Redmond Ridge Field Conversion | 175%
Ravensdale Field Conversion | 175%
Ravensdale Field Addition | 175%
Big Finn Lacrosse Field Conversion | 150%
Petrovitsky Park | 150%
Lakewood Park | 150%
Black Diamond | 175%
Taylor Mountain | 150%
Pinnacle Peak | 150%
Duthie Hill | 175%
Tolt River Mile 1.1 Acquisition | 100%
San Souci Neighborhood Buyout | 100%
Lower Tolt River Acquisition | 100%
Miller River Home Buyout | 50%
Timber Lane Erosion Buyouts | 50%
Winkelman Revetment | 25%
Lower Russell Levee Setback | 25%
Reddington Levee Setback | 25%
Boeing Levee US ACOE ERP | 25%
Briscoe Levee Setback | 25%
Horseshoe Bend Acquisition and Reconnection | 100%
Countyline to A Street | 100%
Right Bank Levee Setback | 100%
Rainbow Bend Levee Removal and Floodplain Reconnection | 100%
Belmondo Revetment Enhancement Project | 25%
Willowmoor Floodplain Restoration | 100%
Rhode Levee Setback | 25%
Cedar Pre Construction Strategic Acquisition | 50%
Elliot Bridge Levee | 25%
Herzman Levee Setback | 25%
Jan Rd - Rutledge Levee Setback | 25%
Riverbend Mobile Home Park Acquisition | 50%
Tolt River Natural Area Acquisition | 50%
Alpine Manor Mobile Park Acquisistion | 50%

## WQ Benefit Calculation (hidden)
Fill in all yellow fields according to the directions provided.
Water Quality Benefit Calculation
Overview:
The general process for estimating TSS reduction involves calculating three items:
1. Acres of commercial, industrial, low density residential (LDR) and/or high density residential (HDR) land uses addressed by the structural control.
2. Median annual TSS unit area loading rate associated with each land use (derived from data collected under S8.D requirements of the 2007 and 2012 Phase I permits).
3. The percent TSS removal efficiency of the facility as designed.
Ecology may approve other methods of calculating an estimated TSS reduction if the Permittee justifies the method is appropriate for the relevant project type.
Estimated TSS Reduction Formula:
Calculate pre-project TSS loading by using the *Estimated TSS Reduction Formula:
Project Name | Land use category (choose one) | Land use category area contributing to project (acres) | x | Median TSS Unit Area Loading Rate (lbs/acre/year) | x | Stormwater treatment removal efficiency for TSS (%) | = | Estimated TSS Reduction (lbs/year)
Cedar Valley Facility Remediation | LDR | 11.4 | x | 18 | x | 0.8 | = | 164.16
Seola Creek Basin Facility Upgrade and Retrofit | HDR | 304 | x | 164 | x | 0.62 | = | 30910.72
Tuscani Facility Remediation | LDR | 8.2 | x | 18 | x | 0.8 | = | 118.08
Evans Creek Tributary 108 Basin Wide Retrofit Siting |  |  | x | Unknown | x |  | = | N/A
May Creek Tributary 291A Small Basin Retrofit |  |  | x | Unknown | x |  | = | N/A
Aging Pipe Replacement Program | LDR |  | x | 18 | x |  | = | N/A
Fairwood 11 Pipe Replacement | HDR |  | x | 164 | x |  | = | N/A
Fairwood 11 Regional Facility Remediation | HDR |  | x | 164 | x |  | = | N/A
May Valley Sediment Removal | LDR |  | x | 18 | x |  | = | N/A
May Valley, Long Marsh Creek Sediment Removal | LDR |  | x | 18 | x |  | = | N/A
Clough Creek Buyout and Sediment Facility | LDR |  | x | 18 | x |  | = | N/A
North Base Stormwater ISGP Upgrade | Other | 7 | x | Unknown | x |  | = | N/A
Dockton Shoreline Restoration | LDR |  | x | 18 | x |  | = | N/A
Elliot Bridge Restoration | LDR |  | x | 18 | x |  | = | N/A
Big Spring Creek Restoration | LDR |  | x | 18 | x |  | = | N/A
Middle Boise - Evans | LDR |  | x | 18 | x |  | = | N/A
Upper Carlson | LDR |  | x | 18 | x |  | = | N/A
Cove Creek | LDR |  | x | 18 | x |  | = | N/A
Porter Levee Setback | LDR |  | x | 18 | x |  | = | N/A
Kanaskat Reach Restoration | LDR |  | x | 18 | x |  | = | N/A
Pt Robinson Salt Marsh Reconnection | LDR |  | x | 18 | x |  | = | N/A
Auburn Narrows Rd Removal/restoration | LDR |  | x | 18 | x |  | = | N/A
Tolt River Flood Plain Reconnection | LDR |  | x | 18 | x |  | = | N/A
Lower Bear Creek Restoration -Klapp | LDR |  | x | 18 | x |  | = | N/A
Cedar Grove Road Water Quality Pond (1122355) | Other | 4 | x | Unknown | x | 0.8 | = | N/A
Avondale Rd (1122356) | Other | 0.5 | x | Unknown | x | 0.8 | = | N/A
Riverbend (1121224) | Other | 0.25 | x | Unknown | x |  | = | N/A
Military Rd at S 342nd | Other | 0.25 | x | Unknown | x |  | = | N/A
South Park Bridge | Other | 0.25 | x | Unknown | x |  | = | N/A
NE Stossel Ck Wy (1121701) | Other | 0.25 | x | Unknown | x |  | = | N/A
Money Creek Rd (1121702) | Other | 0.25 | x | Unknown | x |  | = | N/A
Kerristan Rd flow dispersion (1121776) | Other | 1 | x | Unknown | x | 0.8 | = | N/A
Jones Rd overflow control (1122907) | Other | 0.25 | x | Unknown | x | 0.8 | = | N/A
Kerriston Culvert (1122354) | Other | 0.25 | x | Unknown | x |  | = | N/A
Covington-Sawyer Rd at 179 Ave SE | Other | 0.25 | x | Unknown | x | 0.8 | = | N/A
Peasley Canyon (1122909) | Other | 0.25 | x | Unknown | x |  | = | N/A
SE David Powell Road Drainage Improvement | Other | 0.25 | x | Unknown | x | 20 | = | N/A
Alvord T Bridge Removal | Other | 0.25 | x | Unknown | x | 100 | = | N/A
1122911 Middle Fork Drainage Improvement | Other | 0.25 | x | Unknown | x | 20 | = | N/A
1122912 Wilderness Rim | Other | 0.25 | x | Unknown | x | 50 | = | N/A
1123183 Dockton Rd | Other | 0.7 | x | Unknown | x | 80 | = | N/A
1123184 Black Diamond Ravensdale Rd | Other | 1 | x | Unknown | x | 80 | = | N/A
1122910 North Fork Road Drainage Improvement | Other |  | x | Unknown | x |  | = | N/A
Isaquah Hobart Road at NE 113th St | Other | 0.5 | x | Unknown | x | 100 | = | N/A
140th Avenue SE at SE Petrovitsky Road | Other | 1 | x | Unknown | x | 80 | = | N/A
Issaquah Hobart Road SE at SE May Valley Road | Other | 0.4 | x | Unknown | x | 80 | = | N/A
Factoria Recycling & Xfer Stn - Detention Vault | Other | 6.4 | x | Unknown | x | 0.87 | = | N/A
Factoria Recycling & Xfer Stn - Permeable Pavement | Other | 0.2 | x | Unknown | x | 0.875 | = | N/A
Factoria Recycling & Xfer Stn - Filtera System | Other | 0.36 | x | Unknown | x | 0.85 | = | N/A
Factoria Recycling & Xfer Stn - Amended Sand Filter Vault | Other | 4.1 | x | Unknown | x | 0.8 | = | N/A
Factoria Recycling & Xfer Stn - Rain Water Harvesting | Other | 1.01 | x | Unknown | x | 0.8 | = | N/A
SMag CSO Control Project Storage Facility | LDR | 0.49 | x | 18 | x | 0.8 | = | 7.056
Kirkland Pump Station Upgrade project |  |  | x | Unknown | x |  | = | N/A
North Beach Pump Station and CSO Control Facility | LDR | 0.08 | x | 18 | x | 0.8 | = | 1.152
Redmond Ridge Field Conversion | LDR | 3 | x | 18 | x | 0.8 | = | 43.2
Ravensdale Field Conversion | LDR | 3 | x | 18 | x | 0.8 | = | 43.2
Ravensdale Field Addition | LDR | 6 | x | 18 | x | 0.8 | = | 86.4
Big Finn Lacrosse Field Conversion | LDR | 3 | x | 18 | x | 0.8 | = | 43.2
Petrovitsky Park | LDR | 5 | x | 18 | x | 0.8 | = | 72
Lakewood Park | Commercial | 1 | x | 598 | x | 0.8 | = | 478.4
Black Diamond | LDR | 1 | x | 18 | x | 0.8 | = | 14.4
Taylor Mountain | LDR | 3 | x | 18 | x | 0.8 | = | 43.2
Pinnacle Peak | LDR | 5 | x | 18 | x | 0.8 | = | 72
Duthie Hill | LDR | 4 | x | 18 | x | 0.8 | = | 57.6
Tolt River Mile 1.1 Acquisition | Other |  | x | Unknown | x |  | = | N/A
San Souci Neighborhood Buyout | Other |  | x | Unknown | x |  | = | N/A
Lower Tolt River Acquisition | LDR |  | x | 18 | x |  | = | N/A
Miller River Home Buyout | LDR |  | x | 18 | x |  | = | N/A
Timber Lane Erosion Buyouts | LDR |  | x | 18 | x |  | = | N/A
Winkelman Revetment | Other |  | x | Unknown | x |  | = | N/A
Lower Russell Levee Setback | Other |  | x | Unknown | x |  | = | N/A
Reddington Levee Setback | Other |  | x |  | x |  | = | N/A
Boeing Levee US ACOE ERP | Other |  | x | Unknown | x |  | = | N/A
Briscoe Levee Setback | Other |  | x | Unknown | x |  | = | N/A
Horseshoe Bend Acquisition and Reconnection | Other |  | x | Unknown | x |  | = | N/A
Countyline to A Street | LDR |  | x | 18 | x |  | = | N/A
Right Bank Levee Setback | LDR |  | x | 18 | x |  | = | N/A
Rainbow Bend Levee Removal and Floodplain Reconnection | Other |  | x | Unknown | x |  | = | N/A
Belmondo Revetment Enhancement Project | Other |  | x | Unknown | x |  | = | N/A
Willowmoor Floodplain Restoration |  |  | x | Unknown | x |  | = | N/A
Rhode Levee Setback | Other |  | x | Unknown | x |  | = | N/A
Cedar Pre Construction Strategic Acquisition | LDR |  | x | 18 | x |  | = | N/A
Elliot Bridge Levee | Other |  | x | Unknown | x |  | = | N/A
Herzman Levee Setback | Other |  | x | Unknown | x |  | = | N/A
Jan Rd - Rutledge Levee Setback | Other |  | x | Unknown | x |  | = | N/A
Riverbend Mobile Home Park Acquisition | LDR |  | x | 18 | x |  | = | N/A
Tolt River Natural Area Acquisition | LDR |  | x | 18 | x |  | = | N/A
Alpine Manor Mobile Park Acquisistion | LDR |  | x | 18 | x |  | = | N/A
*For maintenance projects involving solids removal, estimated reduction is the estimated dry weight of total solids (TS) removed in pounds.
Enter the Estimated TSS (or TS) Reduction number in the Appendix 11 reporting table under “WQ Benefit (Est. TSS or TS reduction lbs/yr)”.
Note on B16: Keune, Jennifer: Consistent with Ecology method applied to site selection process for S8.D.
Note on C16: Keune, Jennifer: Total acreage served by project.
Note on A108: Keune, Jennifer: Automated formula takes care of this.

## Hydro Benefit Calculation (hidden)
Fill in all yellow fields according to the directions provided.
Hydro Benefit Calculation
Select the appropriate Hydro Benefit option and enter the corresponding number under the Hydro Benefit Option # in the table:
Option #1 - Standard Flow Control Requirement: Enter the hydro benefit number in the reporting table under “Hydro Benefit (Est. Avg. % flow reduction)” equal to the project’s volume ratio, up to 100%. Refer to Volume Ratio Calculation.
Option #2 – LID Performance Standard: Enter the hydro benefit number in the reporting table under “Hydro Benefit (Est. Avg. % flow reduction)” according to the following:
#2a. 100% if the project meets the LID Performance Standard in Appendix 1, Section 4.5.
#2b. 100% if the project uses Full Dispersion functionally equivalent to BMP T 5.30 in Chapter 5 of Volume V of the Stormwater Management Manual for Western Washington.
#2c. Equal to the project’s volume ratio, up to 100%. Refer to Volume Ratio Calculation.
Volume Ratio Calculation:
The general process involves calculating two volumes:
• Actual storage volume provided by the project: This is the total volume of a detention/retention storage facility regardless of whether the volume was created through construction of a new facility or through expansion on an existing facility.
• Volume required if the project had to meet the Standard Flow Control Requirement or LID Performance Standard: Determine using the Western Washington Hydrology Model (WWHM) (or other approved models or other approved pond sizing methodologies providing comparable data) and assuming a forested pre-developed condition1 the amount of detention/retention storage required to match developed discharge durations to pre-developed durations for the range of pre-developed discharge rates from either:
o Option #1: 50% of the 2-year peak flow up to the full 50-year peak flow.
o Option #2: 8% of the 2-year peak flow up to 50% of the 2-year peak flow.
The calculation compares the new or increased storage volume created by the project to the detention/retention storage volume that would be required under the Standard Flow Control Requirement or LID Performance Standard:
Actual volume provided by the project |  |  |  |  | X | 100 | = | Volume Ratio
Volume required if the project had to meet the Standard Flow Control Requirement or LID Performance Standard
Project Name | Option | Actual Volume (gal) | Volume Req'd if new (gal) | Volume Ratio
Cedar Valley Facility Remediation | 1 | 73043.4783 | 73043.4783 | 100
Seola Creek Basin Facility Upgrade and Retrofit | 1 | 2775562.2189 | 15673763.1184 | 17.7083
Tuscani Facility Remediation | 1 | 123680.6597 | 123680.6597 | 100
Evans Creek Tributary 108 Basin Wide Retrofit Siting |  |  |  | N/A
May Creek Tributary 291A Small Basin Retrofit |  |  |  | N/A
Aging Pipe Replacement Program |  |  |  | N/A
Fairwood 11 Pipe Replacement |  |  |  | N/A
Fairwood 11 Regional Facility Remediation |  |  |  | N/A
May Valley Sediment Removal |  |  |  | N/A
May Valley, Long Marsh Creek Sediment Removal |  |  |  | N/A
Clough Creek Buyout and Sediment Facility |  |  |  | N/A
North Base Stormwater ISGP Upgrade |  |  |  | N/A
Dockton Shoreline Restoration |  |  |  | N/A
Elliot Bridge Restoration |  |  |  | N/A
Big Spring Creek Restoration |  |  |  | N/A
Middle Boise - Evans |  |  |  | N/A
Upper Carlson |  |  |  | N/A
Cove Creek |  |  |  | N/A
Porter Levee Setback |  |  |  | N/A
Kanaskat Reach Restoration |  |  |  | N/A
Pt Robinson Salt Marsh Reconnection |  |  |  | N/A
Auburn Narrows Rd Removal/restoration |  |  |  | N/A
Tolt River Flood Plain Reconnection |  |  |  | N/A
Lower Bear Creek Restoration -Klapp |  |  |  | N/A
Cedar Grove Road Water Quality Pond (1122355) |  |  |  | N/A
Avondale Rd (1122356) | 2a |  |  | 100
Riverbend (1121224) |  |  |  | N/A
Military Rd at S 342nd | 2a |  |  | 100
South Park Bridge | 2a |  |  | 100
NE Stossel Ck Wy (1121701) |  |  |  | N/A
Money Creek Rd (1121702) |  |  |  | N/A
Kerristan Rd flow dispersion (1121776) | 2b |  |  | 100
Jones Rd overflow control (1122907) |  |  |  | N/A
Kerriston Culvert (1122354) |  |  |  | N/A
Covington-Sawyer Rd at 179 Ave SE | 2a |  |  | 100
Peasley Canyon (1122909) |  |  |  | N/A
SE David Powell Road Drainage Improvement |  |  |  | N/A
Alvord T Bridge Removal |  |  |  | N/A
1122911 Middle Fork Drainage Improvement |  |  |  | N/A
1122912 Wilderness Rim |  |  |  | N/A
1123183 Dockton Rd | 2a |  |  | 100
1123184 Black Diamond Ravensdale Rd | 2a |  |  | 100
1122910 North Fork Road Drainage Improvement |  |  |  | N/A
Isaquah Hobart Road at NE 113th St | 2a |  |  | 100
140th Avenue SE at SE Petrovitsky Road |  |  |  | N/A
Issaquah Hobart Road SE at SE May Valley Road |  |  |  | N/A
Factoria Recycling & Xfer Stn - Detention Vault | 2a | 1500000 | 1500000 | 100
Factoria Recycling & Xfer Stn - Permeable Pavement | 2a | 26100 | 26100 | 100
Factoria Recycling & Xfer Stn - Filtera System | 2a | 36495 | 36495 | 100
Factoria Recycling & Xfer Stn - Amended Sand Filter Vault | 2a | 126234 | 126234 | 100
Factoria Recycling & Xfer Stn - Rain Water Harvesting | 2a | 42000 | 42000 | 100
SMag CSO Control Project Storage Facility | 2c | 106820 | 106820 | 100
Kirkland Pump Station Upgrade project | 2a |  |  | 100
North Beach Pump Station and CSO Control Facility | 2c | 57 |  | N/A
Redmond Ridge Field Conversion |  |  |  | N/A
Ravensdale Field Conversion |  |  |  | N/A
Ravensdale Field Addition |  |  |  | N/A
Big Finn Lacrosse Field Conversion |  |  |  | N/A
Petrovitsky Park |  |  |  | N/A
Lakewood Park | 1 | 14679.5 | 14679.5 | 100
Black Diamond | 2b |  |  | 100
Taylor Mountain | 2b |  |  | 100
Pinnacle Peak | 2b |  |  | 100
Duthie Hill | 2b |  |  | 100
Tolt River Mile 1.1 Acquisition |  |  |  | N/A
San Souci Neighborhood Buyout |  |  |  | N/A
Lower Tolt River Acquisition |  |  |  | N/A
Miller River Home Buyout |  |  |  | N/A
Timber Lane Erosion Buyouts |  |  |  | N/A
Winkelman Revetment |  |  |  | N/A
Lower Russell Levee Setback |  |  |  | N/A
Reddington Levee Setback |  |  |  | N/A
Boeing Levee US ACOE ERP |  |  |  | N/A
Briscoe Levee Setback |  |  |  | N/A
Horseshoe Bend Acquisition and Reconnection |  |  |  | N/A
Countyline to A Street |  |  |  | N/A
Right Bank Levee Setback |  |  |  | N/A
Rainbow Bend Levee Removal and Floodplain Reconnection |  |  |  | N/A
Belmondo Revetment Enhancement Project |  |  |  | N/A
Willowmoor Floodplain Restoration |  |  |  | N/A
Rhode Levee Setback |  |  |  | N/A
Cedar Pre Construction Strategic Acquisition |  |  |  | N/A
Elliot Bridge Levee |  |  |  | N/A
Herzman Levee Setback |  |  |  | N/A
Jan Rd - Rutledge Levee Setback |  |  |  | N/A
Riverbend Mobile Home Park Acquisition |  |  |  | N/A
Tolt River Natural Area Acquisition |  |  |  | N/A
Alpine Manor Mobile Park Acquisistion |  |  |  | N/A
1 Use forested land cover as the pre-developed condition unless one of the following applies:
• Reasonable, historic information is available that indicates the site was prairie prior to settlement (modeled as “pasture” in the WWHM).
• The drainage area of the immediate stream and all subsequent downstream basins have had at least 40% total impervious area since 1985. In this case the pre-developed condition to be matched shall be the existing land cover condition. Where basin-specific studies determine a stream channel to be unstable, even though the above criterion is met, the pre-developed condition assumption shall be the “historic” land cover condition, or a land cover condition commensurate with achieving a target flow regime identified by an approved basin study.
Note on G77: Keune, Jennifer: Overrode formula to avoid Div/0 error.

## TSS Loading Rates & Lists (hidden)
TSS loading rates by land use category as calculated using median values derived from S8.D monitoring conducted under previous permits.
| Commercial | HDR | LDR
2010 | 598 | 89 | 32.4
2011 | 1910 | 656 | 23.9
2012 | NA | 52.9 | 6.29
2013 | 239 | 239 | 12.1
Median value | 598 | 164 | 18
Notes:
All values shown in pounds/acre/year
NA - Not available
Land use category list |  |  | Retrofit incentives list | Hydrobenefit Option # | Monitoring Planned
Commercial |  |  | 0.25 | 1 | Yes
HDR |  |  | 0.5 | 2a | No
LDR |  |  | 1 | 2b
Other |  |  | 1.25 | 2c
1.5
1.75
2